## test_plan (15)
Seq # | Station Type | Station Name | Test Sequence | Port | Proc # | Area | Area Category | Stn Opts+ | Stn Opts- | Status | Tested @ | Start Time | Test Time | Comments
2 | ET53925 | HiPot EI | RST |  | 3 | 2 | 2 |  |  | CLEARED |  |  |  | D (Group t); G (Build It)
3 | ET55946 | Align-X | Download | CPU | 2 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-07-29 01:13 | 0:01 | A; G (Build It)
5 | ET55946 | Align-X | Initialization | CPU | 2 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-24 13:25 | 0:10 | A; G (Build It)
6 | ET55946 | Align-X | Initialization | CPU | 3 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-11-06 13:33 | 0:00 | A; G (Build It)
7 | ET55946 | Align-X | Download | CPU | 4 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-12 18:39 | 0:18 | A; G (Build It)
8 | ET55946 | Align-X | Functional Tests | RF1 | 3 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-12 18:59 | 0:31 | A; G (Build It); Y (M9884A - CHANNEL 1)
9 | ET55946 | Align-X | Functional Tests | RF1 | 2 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-16 05:21 | 0:13 | A; G (Build It); Y (M9884A - CHANNEL 1)
11 | ET55946 | Align-X | Functional Tests | RF1 | 4 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-12 21:07 | 2:35 | A; G (Build It); Y (M9884A - CHANNEL 1)
12 | ET55946 | Align-X | Functional Tests | RF1 | 40 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2025-12-18 17:30 | 0:15 | A; G (Build It); Y (M9884A - CHANNEL 1)
13 | ET55946 | Align-X | Functional Tests | RF2 | 3 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-12-24 15:02 | 0:11 | A; G (Build It); Y (M9884A - CHANNEL 2)
14 | ET55946 | Align-X | Functional Tests | RF2 | 2 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-12-24 15:15 | 0:03 | A; G (Build It); Y (M9884A - CHANNEL 2)
15 | ET55946 | Align-X | Functional Tests | RF2 | 4 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-12-31 09:55 | 2:47 | A; G (Build It); Y (M9884A - CHANNEL 2)
16 | ET55946 | Align-X | Functional Tests | RF2 | 40 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-12-31 12:43 | 0:13 | A; G (Build It); Y (M9884A - CHANNEL 2)
25 | ET55946 | Align-X | Functional Tests | CPU | 9 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-12 23:46 | 0:10 | A; G (Build It); I (PCH); Y (M9884A - CHANNEL 1)
26 | ET55946 | Align-X | Functional Tests | CPU | 15 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-12 23:59 | 0:10 | A; G (Build It)
27 | ET55946 | Align-X | Functional Tests | CPU | 30 | 2 | 2 |  |  | PASSED | gdrss3-32 | 2026-01-15 22:28 | 0:40 | A; G (Build It); I (PCH)
28 | ET55946 | Align-X | Functional Tests | CPU | 31 | 2 | 2 |  |  | PASSED | gdrss3-32 | 2026-01-16 01:50 | 0:24 | A; G (Build It); I (PCH)
31 | ET57033 | PNA-X | Adjustments | RF2 | 4 | 2 | 2 | 256 |  | PASSED | gdrss3-04 | 2025-12-31 16:44 | 2:28 | A; M (Diversity group A); Y (M9884A - CHANNEL 2)
32 | ET57033 | PNA-X | Adjustments | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-04 | 2025-12-31 19:25 | 2:38 | A; I (514); M (Diversity group B); Y (M9884A - CHANNEL 2)
33 | ET57033 | PNA-X | Adjustments | RF2 | 6 | 2 | 2 | 512 |  | PASSED | gdrss3-68 | 2026-01-01 07:48 | 10:53 | A; I (532); M (Diversity group C); Y (M9884A - CHANNEL 2)
37 | ET57033 | PNA-X | Adjustments | RF1 | 4 | 2 | 2 | 256 |  | PASSED | gdrss3-68 | 2026-01-13 09:12 | 5:47 | A; M (Diversity group A); Y (M9884A - CHANNEL 1)
38 | ET57033 | PNA-X | Adjustments | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-68 | 2026-01-13 14:59 | 2:39 | A; I (514); M (Diversity group B); Y (M9884A - CHANNEL 1)
39 | ET57033 | PNA-X | Adjustments | RF1 | 6 | 2 | 2 | 512 |  | PASSED | gdrss3-68 | 2026-01-13 19:18 | 14:38 | A; I (532); M (Diversity group C); Y (M9884A - CHANNEL 1)
43 | ET57033 | PNA-X | Phase Measurements | RF1 | 112 | 2 | 2 | 256 |  | PASSED | gdrss3-10 | 2026-01-14 11:02 | 1:36 | I (002); K (Dependency group F parent); M (Diversity group D); Y (M9884A - CHANNEL 1)
44 | ET57033 | PNA-X | Phase Measurements | RF1 | 212 | 2 | 2 |  |  | PASSED | gdrss3-10 | 2026-01-14 12:42 | 1:56 | I (002;514 - all); K (Dependency group G parent); M (Diversity group E); Y (M9884A - CHANNEL 1)
45 | ET57033 | PNA-X | Phase Measurements | RF1 | 312 | 2 | 2 | 512 |  | PASSED | gdrss111 | 2026-01-14 18:11 | 12:26 | I (002;532 - all); K (Dependency group H parent); M (Diversity group F); Y (M9884A - CHANNEL 1)
46 | ET57033 | PNA-X | Phase Measurements | RF2 | 121 | 2 | 2 | 256 |  | PASSED | gdrss3-68 | 2026-01-01 18:44 | 1:11 | I (002); K (Dependency group F parent); M (Diversity group D); Y (M9884A - CHANNEL 2)
47 | ET57033 | PNA-X | Phase Measurements | RF2 | 221 | 2 | 2 |  |  | PASSED | gdrss3-68 | 2026-01-02 07:08 | 1:26 | I (002;514 - all); K (Dependency group G parent); M (Diversity group E); Y (M9884A - CHANNEL 2)
48 | ET57033 | PNA-X | Phase Measurements | RF2 | 321 | 2 | 2 | 512 |  | PASSED | gdrss3-68 | 2026-01-02 09:04 | 1:10 | I (002;532 - all); K (Dependency group H parent); M (Diversity group F); Y (M9884A - CHANNEL 2)
68 | ET54730 | ACLR-Testing | Adjustments | RF1 | 13 | 2 | 2 | 114688 |  | PASSED | gdrss3-55 | 2026-01-16 08:32 | 4:36 | E; I (532); Y (M9884A - CHANNEL 1)
70 | ET54730 | ACLR-Testing | Adjustments | RF2 | 13 | 2 | 2 | 114688 |  | PASSED | gdrss3-55 | 2026-01-02 19:08 | 6:31 | E; I (532); Y (M9884A - CHANNEL 2)
87 | ET43064 | YS Loading Gate | LoadingGateTest | CPU | 2 | 2 | 2 |  |  | PASSED | ys2gate70 | 2026-01-23 16:57 | 0:04 | B
88 | Insert test plan: M9884A 1E62340686 | B; C; Q
89 | ET57033 | PNA-X | Functional Tests | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-17 10:39 | 0:13 | Y (M9884A - CHANNEL 1)
90 | ET57033 | PNA-X | Functional Tests | RF1 | 40 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-17 10:54 | 0:12 | Y (M9884A - CHANNEL 1)
91 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 4 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-17 11:07 | 1:58 | I (532); K (Dependency group I parent); M (Diversity group C); Y (M9884A - CHANNEL 1)
92 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 34 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-17 13:06 | 0:05 | I (532); J (1EC); K (Dependency group I child); Y (M9884A - CHANNEL 1)
95 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 74 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-17 13:14 | 0:16 | I (532); K (Dependency group I child); Y (M9884A - CHANNEL 1)
96 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 3 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-17 13:30 | 0:22 | I (514); K (Dependency group J parent); M (Diversity group B); Y (M9884A - CHANNEL 1)
97 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 33 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-17 13:59 | 0:04 | I (514); J (1EB); K (Dependency group J child); Y (M9884A - CHANNEL 1)
100 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 73 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-17 14:05 | 0:14 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 1)
102 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 2 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-17 14:21 | 0:22 | K (Dependency group K parent); M (Diversity group A); Y (M9884A - CHANNEL 1)
103 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 22 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-17 14:44 | 1:22 | E; Y (M9884A - CHANNEL 1)
104 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 32 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-17 16:14 | 0:34 | J (1EA); K (Dependency group K child); Y (M9884A - CHANNEL 1)
107 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 72 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-17 16:49 | 0:22 | K (Dependency group K child); Y (M9884A - CHANNEL 1)
109 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF1 | 9 | 2 | 2 | 32768 |  | PASSED | gdrss3-51 | 2026-01-17 18:58 | 0:17 | I (554); K (Dependency group I child); Y (M9884A - CHANNEL 1)
110 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF1 | 8 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-17 19:19 | 0:49 | I (532); K (Dependency group I child); Y (M9884A - CHANNEL 1)
111 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF1 | 54 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-17 20:10 | 0:46 | I (554); J (SMP); Y (M9884A - CHANNEL 1)
113 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF1 | 7 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 02:45 | 1:13 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 1)
116 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF1 | 6 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 04:00 | 0:35 | K (Dependency group K child); Y (M9884A - CHANNEL 1)
119 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF1 | 9 | 2 | 2 |  |  | PASSED | pnoise104 | 2026-01-19 14:29 | 0:48 | I (ST5); K (Dependency group V parent); Y (M9884A - CHANNEL 1)
123 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF1 | 44 | 2 | 2 |  |  | PASSED | pnoise104 | 2026-01-19 15:18 | 0:20 | I (532;ST5 - all); K (Dependency group V child); Y (M9884A - CHANNEL 1)
124 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF1 | 43 | 2 | 2 |  |  | PASSED | pnoise104 | 2026-01-19 15:46 | 0:14 | I (514;ST5 - all); K (Dependency group V child); Y (M9884A - CHANNEL 1)
125 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF1 | 42 | 2 | 2 |  |  | PASSED | pnoise104 | 2026-01-19 16:06 | 0:31 | I (ST5); K (Dependency group V child); Y (M9884A - CHANNEL 1)
126 | ET54730 | ACLR-Testing | Channel Flatness | RF1 | 8 | 2 | 2 | 98304 | 32 | PASSED | gdrss3-59 | 2026-01-16 18:30 | 0:07 | I (554); Y (M9884A - CHANNEL 1)
127 | ET54730 | ACLR-Testing | Channel Flatness | RF1 | 7 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-59 | 2026-01-16 22:26 | 0:10 | I (532); Y (M9884A - CHANNEL 1)
128 | ET54730 | ACLR-Testing | Channel Flatness | RF1 | 6 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-55 | 2026-01-16 15:10 | 0:02 | I (514); Y (M9884A - CHANNEL 1)
129 | ET54730 | ACLR-Testing | Channel Flatness | RF1 | 3 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-55 | 2026-01-16 15:13 | 0:02 | Y (M9884A - CHANNEL 1)
130 | ET54730 | ACLR-Testing | Functional Tests | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 04:36 | 0:03 | Y (M9884A - CHANNEL 1)
131 | ET54730 | ACLR-Testing | Phase Measurements | RF1 | 38 | 2 | 2 | 32768 | 32 | PASSED | gdrss3-13 | 2026-01-21 08:13 | 0:07 | I (554); K (Dependency group H child); Y (M9884A - CHANNEL 1)
132 | ET54730 | ACLR-Testing | Phase Measurements | RF1 | 37 | 2 | 2 |  | 32 | PASSED | gdrss3-17 | 2026-01-18 04:40 | 0:17 | I (532); K (Dependency group H child); Y (M9884A - CHANNEL 1)
133 | ET57033 | PNA-X | Phase Measurements | RF1 | 35 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-17 17:12 | 0:30 | I (532); K (Dependency group H child); M (Diversity group F); Y (M9884A - CHANNEL 1)
134 | ET54730 | ACLR-Testing | Phase Measurements | RF1 | 34 | 2 | 2 |  | 32 | PASSED | gdrss3-17 | 2026-01-18 05:00 | 0:11 | I (514); K (Dependency group G child); Y (M9884A - CHANNEL 1)
135 | ET57033 | PNA-X | Phase Measurements | RF1 | 33 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-18 14:33 | 0:25 | I (514); K (Dependency group G child); M (Diversity group E); Y (M9884A - CHANNEL 1)
136 | ET54730 | ACLR-Testing | Phase Measurements | RF1 | 32 | 2 | 2 |  | 32 | PASSED | gdrss3-17 | 2026-01-18 05:12 | 0:15 | K (Dependency group F child); Y (M9884A - CHANNEL 1)
137 | ET57033 | PNA-X | Phase Measurements | RF1 | 31 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-18 14:59 | 0:16 | K (Dependency group F child); M (Diversity group D); Y (M9884A - CHANNEL 1)
138 | ET55857 | X-Mod | Functional Tests | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-22 | 2026-01-20 06:45 | 0:03 | Y (M9884A - CHANNEL 1)
139 | ET55857 | X-Mod | Switching Speed | RF1 | 5 | 2 | 2 | 64 |  | PASSED | gdrss3-22 | 2026-01-20 06:49 | 2:45 | I (532); Y (M9884A - CHANNEL 1)
140 | ET55857 | X-Mod | Switching Speed | RF1 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-20 09:35 | 0:51 | I (514); Y (M9884A - CHANNEL 1)
141 | ET55857 | X-Mod | Switching Speed | RF1 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-20 10:27 | 0:19 | Y (M9884A - CHANNEL 1)
142 | ET54730 | ACLR-Testing | Pulse Modulation | RF1 | 12 | 2 | 2 | 32768 |  | PASSED | gdrss3-13 | 2026-01-21 08:21 | 0:13 | I (554); Y (M9884A - CHANNEL 1)
143 | ET54730 | ACLR-Testing | Pulse Modulation | RF1 | 11 | 2 | 2 | 8192 | 94 | PASSED | gdrss3-17 | 2026-01-18 05:28 | 0:31 | Y (M9884A - CHANNEL 1)
144 | ET55857 | X-Mod | Pulse Modulation | RF1 | 5 | 2 | 2 | 64 |  | PASSED | gdrss3-22 | 2026-01-20 10:47 | 0:57 | I (532); Y (M9884A - CHANNEL 1)
145 | ET55857 | X-Mod | Pulse Modulation | RF1 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-20 11:45 | 0:27 | I (514); Y (M9884A - CHANNEL 1)
146 | ET55857 | X-Mod | Pulse Modulation | RF1 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-20 12:13 | 0:24 | Y (M9884A - CHANNEL 1)
153 | ET54730 | ACLR-Testing | Spectral | RF1 | 54 | 2 | 2 | 32768 |  | PASSED | gdrss3-13 | 2026-01-21 08:35 | 3:34 | I (554); Y (M9884A - CHANNEL 1)
154 | ET54730 | ACLR-Testing | Spectral | RF1 | 26 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 06:00 | 0:14 | I (532); Y (M9884A - CHANNEL 1)
155 | ET54730 | ACLR-Testing | Spectral | RF1 | 25 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 06:14 | 0:09 | I (532); Y (M9884A - CHANNEL 1)
156 | ET54730 | ACLR-Testing | Spectral | RF1 | 24 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 06:24 | 1:20 | I (532); Y (M9884A - CHANNEL 1)
157 | ET54730 | ACLR-Testing | Spectral | RF1 | 23 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 07:48 | 0:09 | I (544); Y (M9884A - CHANNEL 1)
158 | ET54730 | ACLR-Testing | Spectral | RF1 | 16 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 07:58 | 0:08 | I (514); Y (M9884A - CHANNEL 1)
159 | ET54730 | ACLR-Testing | Spectral | RF1 | 15 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 08:06 | 0:13 | I (514); Y (M9884A - CHANNEL 1)
160 | ET54730 | ACLR-Testing | Spectral | RF1 | 14 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 08:20 | 0:47 | I (514); Y (M9884A - CHANNEL 1)
161 | ET54730 | ACLR-Testing | Spectral | RF1 | 13 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 09:08 | 0:27 | I (520); Y (M9884A - CHANNEL 1)
162 | ET54730 | ACLR-Testing | Spectral | RF1 | 6 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 09:41 | 0:09 | Y (M9884A - CHANNEL 1)
163 | ET54730 | ACLR-Testing | Spectral | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 09:54 | 0:10 | Y (M9884A - CHANNEL 1)
164 | ET54730 | ACLR-Testing | Spectral | RF1 | 4 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 10:05 | 0:17 | Y (M9884A - CHANNEL 1)
165 | ET54730 | ACLR-Testing | Spectral | RF1 | 3 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-18 19:16 | 0:10 | Y (M9884A - CHANNEL 1)
166 | ET54730 | ACLR-Testing | Acpr | RF1 | 8 | 2 | 2 | 32768 | 32 | PASSED | gdrss3-13 | 2026-01-21 15:21 | 0:14 | I (554); Y (M9884A - CHANNEL 1)
167 | ET54730 | ACLR-Testing | Acpr | RF1 | 7 | 2 | 2 |  | 32 | PASSED | gdrss3-51 | 2026-01-22 03:37 | 1:54 | I (532); Y (M9884A - CHANNEL 1)
168 | ET54730 | ACLR-Testing | Acpr | RF1 | 6 | 2 | 2 |  | 32 | PASSED | gdrss3-13 | 2026-01-21 21:27 | 0:42 | I (514); Y (M9884A - CHANNEL 1)
169 | ET54730 | ACLR-Testing | Acpr | RF1 | 4 | 2 | 2 |  | 32 | PASSED | gdrss3-13 | 2026-01-21 22:10 | 1:51 | Y (M9884A - CHANNEL 1)
170 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 29 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-18 15:18 | 0:04 | E; M (Diversity group A); Y (M9884A - CHANNEL 1)
171 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 21 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-17 17:44 | 0:11 | A; M (Diversity group A); Y (M9884A - CHANNEL 1)
172 | Insert test plan: M9884A 1E62340687 | B; C; I (002); Q
173 | ET57033 | PNA-X | Functional Tests | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-18 10:43 | 0:04 | Y (M9884A - CHANNEL 2)
174 | ET57033 | PNA-X | Functional Tests | RF2 | 40 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-18 10:49 | 0:12 | Y (M9884A - CHANNEL 2)
175 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 4 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-17 17:58 | 0:29 | I (532); K (Dependency group I parent); M (Diversity group C); Y (M9884A - CHANNEL 2)
176 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 34 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-17 18:29 | 0:04 | I (532); J (1EC); K (Dependency group I child); Y (M9884A - CHANNEL 2)
179 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 74 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-17 18:34 | 0:09 | I (532); K (Dependency group I child); Y (M9884A - CHANNEL 2)
180 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 3 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-18 11:03 | 0:21 | I (514); K (Dependency group J parent); M (Diversity group B); Y (M9884A - CHANNEL 2)
181 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 33 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-18 11:25 | 0:04 | I (514); J (1EB); K (Dependency group J child); Y (M9884A - CHANNEL 2)
184 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 73 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-18 11:30 | 0:11 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 2)
186 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 2 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-18 11:42 | 0:22 | K (Dependency group K parent); M (Diversity group A); Y (M9884A - CHANNEL 2)
187 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 22 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-18 12:14 | 1:46 | E; Y (M9884A - CHANNEL 2)
188 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 32 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-18 14:04 | 0:05 | J (1EA); K (Dependency group K child); Y (M9884A - CHANNEL 2)
191 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 72 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-18 14:14 | 0:18 | K (Dependency group K child); Y (M9884A - CHANNEL 2)
193 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF2 | 9 | 2 | 2 | 32768 |  | PASSED | gdrss3-13 | 2026-01-22 00:06 | 0:17 | I (554); K (Dependency group I child); Y (M9884A - CHANNEL 2)
194 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF2 | 8 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-22 05:32 | 0:50 | I (532); K (Dependency group I child); Y (M9884A - CHANNEL 2)
195 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF2 | 54 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-22 06:27 | 0:46 | I (554); J (SMP); Y (M9884A - CHANNEL 2)
197 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF2 | 7 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-22 11:04 | 1:12 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 2)
200 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF2 | 6 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-22 10:22 | 0:37 | K (Dependency group K child); Y (M9884A - CHANNEL 2)
206 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF2 | 44 | 2 | 2 |  |  | PASSED | pnoise104 | 2026-01-19 16:38 | 0:21 | I (532;ST5 - all); K (Dependency group V child); Y (M9884A - CHANNEL 2)
207 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF2 | 43 | 2 | 2 |  |  | PASSED | pnoise104 | 2026-01-19 17:11 | 0:16 | I (514;ST5 - all); K (Dependency group V child); Y (M9884A - CHANNEL 2)
208 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF2 | 42 | 2 | 2 |  |  | PASSED | pnoise104 | 2026-01-19 18:29 | 0:33 | I (ST5); K (Dependency group V child); Y (M9884A - CHANNEL 2)
209 | ET54730 | ACLR-Testing | Channel Flatness | RF2 | 8 | 2 | 2 | 98304 | 32 | PASSED | gdrss3-59 | 2026-01-17 02:26 | 0:22 | I (554); Y (M9884A - CHANNEL 2)
210 | ET54730 | ACLR-Testing | Channel Flatness | RF2 | 7 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-59 | 2026-01-16 21:56 | 0:23 | I (532); Y (M9884A - CHANNEL 2)
211 | ET54730 | ACLR-Testing | Channel Flatness | RF2 | 6 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-59 | 2026-01-16 22:21 | 0:02 | I (514); Y (M9884A - CHANNEL 2)
212 | ET54730 | ACLR-Testing | Channel Flatness | RF2 | 3 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-59 | 2026-01-16 22:24 | 0:01 | Y (M9884A - CHANNEL 2)
213 | ET54730 | ACLR-Testing | Functional Tests | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-22 12:17 | 0:03 | Y (M9884A - CHANNEL 2)
214 | ET54730 | ACLR-Testing | Phase Measurements | RF2 | 38 | 2 | 2 | 32768 | 32 | PASSED | gdrss3-14 | 2026-01-23 01:25 | 0:06 | I (554); K (Dependency group H child); Y (M9884A - CHANNEL 2)
215 | ET54730 | ACLR-Testing | Phase Measurements | RF2 | 37 | 2 | 2 |  | 32 | PASSED | gdrss3-52 | 2026-01-22 13:20 | 0:19 | I (532); K (Dependency group H child); Y (M9884A - CHANNEL 2)
216 | ET57033 | PNA-X | Phase Measurements | RF2 | 35 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-18 15:24 | 0:31 | I (532); K (Dependency group H child); M (Diversity group F); Y (M9884A - CHANNEL 2)
217 | ET54730 | ACLR-Testing | Phase Measurements | RF2 | 34 | 2 | 2 |  | 32 | PASSED | gdrss3-52 | 2026-01-22 13:40 | 0:11 | I (514); K (Dependency group G child); Y (M9884A - CHANNEL 2)
218 | ET57033 | PNA-X | Phase Measurements | RF2 | 33 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-18 17:45 | 0:22 | I (514); K (Dependency group G child); M (Diversity group E); Y (M9884A - CHANNEL 2)
219 | ET54730 | ACLR-Testing | Phase Measurements | RF2 | 32 | 2 | 2 |  | 32 | PASSED | gdrss3-17 | 2026-01-22 19:21 | 0:17 | K (Dependency group F child); Y (M9884A - CHANNEL 2)
220 | ET57033 | PNA-X | Phase Measurements | RF2 | 31 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-18 18:17 | 0:14 | K (Dependency group F child); M (Diversity group D); Y (M9884A - CHANNEL 2)
221 | ET55857 | X-Mod | Functional Tests | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-22 | 2026-01-20 12:38 | 0:03 | Y (M9884A - CHANNEL 2)
222 | ET55857 | X-Mod | Switching Speed | RF2 | 5 | 2 | 2 | 64 |  | PASSED | gdrss3-22 | 2026-01-24 05:07 | 1:49 | I (532); Y (M9884A - CHANNEL 2)
223 | ET55857 | X-Mod | Switching Speed | RF2 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-24 06:57 | 0:37 | I (514); Y (M9884A - CHANNEL 2)
224 | ET55857 | X-Mod | Switching Speed | RF2 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-24 07:35 | 0:18 | Y (M9884A - CHANNEL 2)
225 | ET54730 | ACLR-Testing | Pulse Modulation | RF2 | 12 | 2 | 2 | 32768 |  | PASSED | gdrss3-14 | 2026-01-23 18:55 | 0:13 | I (554); Y (M9884A - CHANNEL 2)
226 | ET54730 | ACLR-Testing | Pulse Modulation | RF2 | 11 | 2 | 2 | 8192 | 94 | PASSED | gdrss3-17 | 2026-01-22 19:44 | 0:32 | Y (M9884A - CHANNEL 2)
227 | ET55857 | X-Mod | Pulse Modulation | RF2 | 5 | 2 | 2 | 64 |  | PASSED | gdrss3-22 | 2026-01-24 07:53 | 0:57 | I (532); Y (M9884A - CHANNEL 2)
228 | ET55857 | X-Mod | Pulse Modulation | RF2 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-24 08:51 | 0:27 | I (514); Y (M9884A - CHANNEL 2)
229 | ET55857 | X-Mod | Pulse Modulation | RF2 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-24 09:18 | 0:24 | Y (M9884A - CHANNEL 2)
236 | ET54730 | ACLR-Testing | Spectral | RF2 | 54 | 2 | 2 | 32768 |  | PASSED | gdrss3-14 | 2026-01-23 19:11 | 0:27 | I (554); Y (M9884A - CHANNEL 2)
237 | ET54730 | ACLR-Testing | Spectral | RF2 | 26 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-22 20:17 | 0:14 | I (532); Y (M9884A - CHANNEL 2)
238 | ET54730 | ACLR-Testing | Spectral | RF2 | 25 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-22 20:31 | 0:09 | I (532); Y (M9884A - CHANNEL 2)
239 | ET54730 | ACLR-Testing | Spectral | RF2 | 24 | 2 | 2 |  |  | PASSED | gdrss3-52 | 2026-01-23 04:29 | 1:20 | I (532); Y (M9884A - CHANNEL 2)
240 | ET54730 | ACLR-Testing | Spectral | RF2 | 23 | 2 | 2 |  |  | PASSED | gdrss3-52 | 2026-01-23 05:50 | 0:09 | I (544); Y (M9884A - CHANNEL 2)
241 | ET54730 | ACLR-Testing | Spectral | RF2 | 16 | 2 | 2 |  |  | PASSED | gdrss3-52 | 2026-01-23 06:00 | 0:09 | I (514); Y (M9884A - CHANNEL 2)
242 | ET54730 | ACLR-Testing | Spectral | RF2 | 15 | 2 | 2 |  |  | PASSED | gdrss3-52 | 2026-01-23 06:09 | 0:13 | I (514); Y (M9884A - CHANNEL 2)
243 | ET54730 | ACLR-Testing | Spectral | RF2 | 14 | 2 | 2 |  |  | PASSED | gdrss3-52 | 2026-01-23 06:22 | 0:48 | I (514); Y (M9884A - CHANNEL 2)
244 | ET54730 | ACLR-Testing | Spectral | RF2 | 13 | 2 | 2 |  |  | PASSED | gdrss3-52 | 2026-01-23 07:14 | 0:25 | I (520); Y (M9884A - CHANNEL 2)
245 | ET54730 | ACLR-Testing | Spectral | RF2 | 6 | 2 | 2 |  |  | PASSED | gdrss3-52 | 2026-01-23 07:40 | 0:09 | Y (M9884A - CHANNEL 2)
246 | ET54730 | ACLR-Testing | Spectral | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-52 | 2026-01-23 07:50 | 0:10 | Y (M9884A - CHANNEL 2)
247 | ET54730 | ACLR-Testing | Spectral | RF2 | 4 | 2 | 2 |  |  | PASSED | gdrss3-59 | 2026-01-23 14:55 | 0:18 | Y (M9884A - CHANNEL 2)
248 | ET54730 | ACLR-Testing | Spectral | RF2 | 3 | 2 | 2 |  |  | PASSED | gdrss3-14 | 2026-01-23 19:39 | 0:10 | Y (M9884A - CHANNEL 2)
249 | ET54730 | ACLR-Testing | Acpr | RF2 | 8 | 2 | 2 | 32768 | 32 | PASSED | gdrss3-14 | 2026-01-23 19:50 | 0:09 | I (554); Y (M9884A - CHANNEL 2)
250 | ET54730 | ACLR-Testing | Acpr | RF2 | 7 | 2 | 2 |  | 32 | PASSED | gdrss3-14 | 2026-01-23 20:00 | 1:53 | I (532); Y (M9884A - CHANNEL 2)
251 | ET54730 | ACLR-Testing | Acpr | RF2 | 6 | 2 | 2 |  | 32 | PASSED | gdrss3-14 | 2026-01-23 21:59 | 0:41 | I (514); Y (M9884A - CHANNEL 2)
252 | ET54730 | ACLR-Testing | Acpr | RF2 | 4 | 2 | 2 |  | 32 | PASSED | gdrss3-19 | 2026-01-24 00:35 | 1:52 | Y (M9884A - CHANNEL 2)
253 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 29 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-18 18:35 | 0:04 | E; M (Diversity group A); Y (M9884A - CHANNEL 2)
254 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 21 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-18 18:43 | 0:10 | A; M (Diversity group A); Y (M9884A - CHANNEL 2)
422 | ET54791 | POSTPONEMENT | Functional Tests | CPU | 16 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-01-25 10:04 | 0:02 | A; G (Ship It)
423 | ET54791 | POSTPONEMENT | MCS3 Reconfig | CPU | 6 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-27 11:16 | 0:05 | A; G (Ship It); I (PCH)
424 | ET54791 | POSTPONEMENT | MCS3 Reconfig | CPU | 7 | 2 | 2 |  |  | PASSED | gdrss24 | 2026-01-26 15:12 | 0:08 | A; G (Ship It)
425 | ET54791 | POSTPONEMENT | CustomerInit | CPU | 2 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-26 15:28 | 0:03 | A; G (Ship It)
426 | ET54791 | POSTPONEMENT | CustomerInit | CPU | 3 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-26 15:40 | 0:00 | A; G (Ship It)
427 | ET54791 | POSTPONEMENT | Functional Tests | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-26 15:47 | 0:04 | A; G (Ship It); Y (M9884A - CHANNEL 1)
428 | ET54791 | POSTPONEMENT | Functional Tests | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-26 16:06 | 0:03 | A; G (Ship It); Y (M9884A - CHANNEL 2)
431 | ET54791 | POSTPONEMENT | Functional Tests | RF1 | 17 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-26 16:14 | 0:02 | A; G (Ship It); Y (M9884A - CHANNEL 1)
432 | ET54791 | POSTPONEMENT | Functional Tests | RF2 | 17 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-26 16:19 | 0:01 | A; G (Ship It); Y (M9884A - CHANNEL 2)
435 | ET54791 | POSTPONEMENT | FinalConfiguration | CPU | 2 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-26 16:22 | 0:01 | A; G (Ship It); J (A6J;AMG - any)
436 | ET54791 | POSTPONEMENT | Functional Tests | CPU | 34 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-01-26 16:24 | 0:00 | A; G (Ship It)
438 | ET53925 | HiPot EI | RST |  | 3 | 2 | 2 |  |  | PASSED | sshipot01 | 2026-01-27 16:42 | 0:01 | G (Ship It)