## test_plan (1)
Seq # | Station Type | Station Name | Test Sequence | Port | Proc # | Area | Area Category | Stn Opts+ | Stn Opts- | Status | Tested @ | Start Time | Test Time | Comments
2 | ET53925 | HiPot EI | RST |  | 3 | 2 | 2 |  |  | CLEARED |  |  |  | D (Group t); G (Build It)
3 | ET55946 | Align-X | Download | CPU | 2 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-08-31 13:05 | 0:01 | A; G (Build It)
5 | ET55946 | Align-X | Initialization | CPU | 2 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-08-31 13:08 | 0:11 | A; G (Build It)
6 | ET55946 | Align-X | Initialization | CPU | 3 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2025-08-31 13:20 | 0:00 | A; G (Build It)
7 | ET55946 | Align-X | Download | CPU | 4 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 08:46 | 0:18 | A; G (Build It)
8 | ET55946 | Align-X | Functional Tests | RF1 | 3 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 10:06 | 0:14 | A; G (Build It); Y (M9884A - CHANNEL 1)
9 | ET55946 | Align-X | Functional Tests | RF1 | 2 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-21 14:25 | 0:17 | A; G (Build It); Y (M9884A - CHANNEL 1)
10 | ET55946 | Align-X | Functional Tests | CPU | 41 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 13:00 | 0:02 | A; G (Build It)
12 | ET55946 | Align-X | Functional Tests | RF1 | 4 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 10:48 | 1:49 | A; G (Build It); Y (M9884A - CHANNEL 1)
13 | ET55946 | Align-X | Functional Tests | RF1 | 40 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 12:38 | 0:15 | A; G (Build It); Y (M9884A - CHANNEL 1)
14 | ET55946 | Align-X | Functional Tests | RF2 | 3 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 13:05 | 0:15 | A; G (Build It); Y (M9884A - CHANNEL 2)
15 | ET55946 | Align-X | Functional Tests | RF2 | 2 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 13:39 | 1:25 | A; G (Build It); Y (M9884A - CHANNEL 2)
16 | ET55946 | Align-X | Functional Tests | RF2 | 4 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 13:44 | 1:25 | A; G (Build It); Y (M9884A - CHANNEL 2)
17 | ET55946 | Align-X | Functional Tests | RF2 | 40 | 2 | 2 |  |  | PASSED | gdrss3-31 | 2026-01-07 15:10 | 0:17 | A; G (Build It); Y (M9884A - CHANNEL 2)
18 | ET55946 | Align-X | Functional Tests | RF3 | 3 | 2 | 2 |  |  | PASSED | gdrss37 | 2026-01-14 10:14 | 0:12 | A; G (Build It); Y (M9884A - CHANNEL 3)
19 | ET55946 | Align-X | Functional Tests | RF3 | 2 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-14 12:22 | 0:03 | A; G (Build It); Y (M9884A - CHANNEL 3)
20 | ET55946 | Align-X | Functional Tests | RF3 | 4 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-14 12:54 | 1:33 | A; G (Build It); Y (M9884A - CHANNEL 3)
21 | ET55946 | Align-X | Functional Tests | RF3 | 40 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-14 14:55 | 0:14 | A; G (Build It); Y (M9884A - CHANNEL 3)
22 | ET55946 | Align-X | Functional Tests | RF4 | 3 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-14 15:10 | 0:13 | A; G (Build It); Y (M9884A - CHANNEL 4)
23 | ET55946 | Align-X | Functional Tests | RF4 | 2 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-27 01:41 | 0:03 | A; G (Build It); Y (M9884A - CHANNEL 4)
24 | ET55946 | Align-X | Functional Tests | RF4 | 4 | 2 | 2 |  |  | PASSED | gdrss3-34 | 2026-01-14 15:34 | 1:28 | A; G (Build It); Y (M9884A - CHANNEL 4)
25 | ET55946 | Align-X | Functional Tests | RF4 | 40 | 2 | 2 |  |  | PASSED | gdrss3-33 | 2026-01-14 18:33 | 1:02 | A; G (Build It); Y (M9884A - CHANNEL 4)
26 | ET55946 | Align-X | Functional Tests | CPU | 9 | 2 | 2 |  |  | PASSED | gdrss3-33 | 2026-01-15 07:13 | 0:06 | A; G (Build It); I (PCH); Y (M9884A - CHANNEL 1)
27 | ET55946 | Align-X | Functional Tests | CPU | 15 | 2 | 2 |  |  | PASSED | gdrss3-33 | 2026-01-15 07:20 | 0:11 | A; G (Build It)
28 | ET55946 | Align-X | Functional Tests | CPU | 30 | 2 | 2 |  |  | PASSED | gdrss3-32 | 2026-01-15 18:30 | 0:17 | A; G (Build It); I (PCH)
29 | ET55946 | Align-X | Functional Tests | CPU | 31 | 2 | 2 |  |  | PASSED | gdrss3-32 | 2026-01-15 18:53 | 0:20 | A; G (Build It); I (PCH)
30 | ET55946 | Align-X | Functional Tests | RF1 | 42 | 2 | 2 |  |  | PASSED | gdrss37 | 2026-03-04 15:41 | 0:02 | A; G (Build It); J (AN1); Y (M9884A - CHANNEL 1)
31 | ET55946 | Align-X | Functional Tests | RF2 | 42 | 2 | 2 |  |  | PASSED | gdrss37 | 2026-03-04 15:44 | 0:00 | A; G (Build It); Y (M9884A - CHANNEL 2)
32 | ET55946 | Align-X | Functional Tests | RF3 | 42 | 2 | 2 |  |  | PASSED | gdrss37 | 2026-03-04 15:47 | 0:00 | A; G (Build It); Y (M9884A - CHANNEL 3)
33 | ET55946 | Align-X | Functional Tests | RF4 | 42 | 2 | 2 |  |  | PASSED | gdrss37 | 2026-03-04 15:49 | 0:00 | A; G (Build It); Y (M9884A - CHANNEL 4)
36 | ET57033 | PNA-X | Adjustments | RF2 | 4 | 2 | 2 | 256 |  | PASSED | gdrss3-10 | 2026-01-16 06:17 | 3:25 | A; M (Diversity group A); Y (M9884A - CHANNEL 2)
37 | ET57033 | PNA-X | Adjustments | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-10 | 2026-01-16 13:48 | 3:23 | A; I (514); M (Diversity group B); Y (M9884A - CHANNEL 2)
42 | ET57033 | PNA-X | Adjustments | RF1 | 4 | 2 | 2 | 256 |  | PASSED | gdrss3-05 | 2026-01-21 15:00 | 3:15 | A; M (Diversity group A); Y (M9884A - CHANNEL 1)
43 | ET57033 | PNA-X | Adjustments | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-05 | 2026-01-21 18:18 | 2:47 | A; I (514); M (Diversity group B); Y (M9884A - CHANNEL 1)
48 | ET57033 | PNA-X | Phase Measurements | RF1 | 112 | 2 | 2 | 256 |  | PASSED | gdrss3-05 | 2026-01-21 22:03 | 1:28 | I (002); K (Dependency group F parent); M (Diversity group D); Y (M9884A - CHANNEL 1)
49 | ET57033 | PNA-X | Phase Measurements | RF1 | 212 | 2 | 2 |  |  | PASSED | gdrss3-05 | 2026-01-21 23:39 | 1:36 | I (002;514 - all); K (Dependency group G parent); M (Diversity group E); Y (M9884A - CHANNEL 1)
51 | ET57033 | PNA-X | Phase Measurements | RF2 | 121 | 2 | 2 | 256 |  | PASSED | gdrss113 | 2026-01-19 13:10 | 2:47 | I (002); K (Dependency group F parent); M (Diversity group D); Y (M9884A - CHANNEL 2)
52 | ET57033 | PNA-X | Phase Measurements | RF2 | 221 | 2 | 2 |  |  | PASSED | gdrss113 | 2026-01-19 16:04 | 1:35 | I (002;514 - all); K (Dependency group G parent); M (Diversity group E); Y (M9884A - CHANNEL 2)
54 | ET57033 | PNA-X | Adjustments | RF4 | 4 | 2 | 2 | 256 |  | PASSED | gdrss3-05 | 2026-01-27 02:02 | 3:22 | A; M (Diversity group A); Y (M9884A - CHANNEL 4)
55 | ET57033 | PNA-X | Adjustments | RF4 | 5 | 2 | 2 |  |  | PASSED | gdrss3-10 | 2026-01-17 10:54 | 3:11 | A; I (514); M (Diversity group B); Y (M9884A - CHANNEL 4)
60 | ET57033 | PNA-X | Adjustments | RF3 | 4 | 2 | 2 | 256 |  | PASSED | gdrss3-10 | 2026-01-16 17:15 | 3:25 | A; M (Diversity group A); Y (M9884A - CHANNEL 3)
61 | ET57033 | PNA-X | Adjustments | RF3 | 5 | 2 | 2 |  |  | PASSED | gdrss113 | 2026-01-17 18:14 | 3:10 | A; I (514); M (Diversity group B); Y (M9884A - CHANNEL 3)
66 | ET57033 | PNA-X | Phase Measurements | RF3 | 134 | 2 | 2 | 256 |  | PASSED | gdrss113 | 2026-01-19 18:29 | 1:32 | I (004); K (Dependency group F parent); M (Diversity group D); Y (M9884A - CHANNEL 3)
67 | ET57033 | PNA-X | Phase Measurements | RF3 | 234 | 2 | 2 |  |  | PASSED | gdrss113 | 2026-01-19 20:17 | 1:33 | I (004;514 - all); K (Dependency group G parent); M (Diversity group E); Y (M9884A - CHANNEL 3)
69 | ET57033 | PNA-X | Phase Measurements | RF4 | 143 | 2 | 2 | 256 |  | PASSED | gdrss113 | 2026-01-19 22:16 | 1:27 | I (004); K (Dependency group F parent); M (Diversity group D); Y (M9884A - CHANNEL 4)
70 | ET57033 | PNA-X | Phase Measurements | RF4 | 243 | 2 | 2 |  |  | PASSED | gdrss113 | 2026-01-20 00:38 | 1:27 | I (004;514 - all); K (Dependency group G parent); M (Diversity group E); Y (M9884A - CHANNEL 4)
72 | ET54730 | ACLR-Testing | Adjustments | RF1 | 11 | 2 | 2 | 81920 |  | PASSED | gdrss3-16 | 2026-01-22 04:40 | 1:49 | E; J (532); Y (M9884A - CHANNEL 1)
74 | ET54730 | ACLR-Testing | Adjustments | RF2 | 11 | 2 | 2 | 81920 |  | PASSED | gdrss3-53 | 2026-01-20 10:20 | 0:43 | E; J (532); Y (M9884A - CHANNEL 2)
76 | ET54730 | ACLR-Testing | Adjustments | RF3 | 11 | 2 | 2 | 81920 |  | PASSED | gdrss3-53 | 2026-01-20 11:06 | 1:20 | E; J (532); Y (M9884A - CHANNEL 3)
78 | ET54730 | ACLR-Testing | Adjustments | RF4 | 11 | 2 | 2 | 81920 |  | PASSED | gdrss3-53 | 2026-01-20 12:29 | 0:54 | E; J (532); Y (M9884A - CHANNEL 4)
104 | ET43064 | YS Loading Gate | LoadingGateTest | CPU | 2 | 2 | 2 |  |  | PASSED | ys2gate70 | 2026-01-31 12:05 | 0:04 | B
105 | Insert test plan: M9884A 1E62340461 | B; C; Q
106 | ET57033 | PNA-X | Functional Tests | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 10:29 | 0:03 | Y (M9884A - CHANNEL 1)
107 | ET57033 | PNA-X | Functional Tests | RF1 | 40 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 10:33 | 0:15 | Y (M9884A - CHANNEL 1)
113 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 3 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 10:51 | 0:28 | I (514); K (Dependency group J parent); M (Diversity group B); Y (M9884A - CHANNEL 1)
114 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 33 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 11:21 | 0:05 | I (514); J (1EB); K (Dependency group J child); Y (M9884A - CHANNEL 1)
117 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 73 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 11:27 | 0:30 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 1)
119 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 2 | 2 | 2 | 256 |  | PASSED | gdrss3-02 | 2026-01-22 11:58 | 0:32 | K (Dependency group K parent); M (Diversity group A); Y (M9884A - CHANNEL 1)
120 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 22 | 2 | 2 | 256 |  | PASSED | gdrss3-02 | 2026-01-22 12:34 | 2:36 | E; Y (M9884A - CHANNEL 1)
121 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 32 | 2 | 2 | 256 |  | PASSED | gdrss3-02 | 2026-01-22 15:13 | 0:06 | J (1EA); K (Dependency group K child); Y (M9884A - CHANNEL 1)
124 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 72 | 2 | 2 | 256 |  | PASSED | gdrss3-02 | 2026-01-22 15:20 | 2:00 | K (Dependency group K child); Y (M9884A - CHANNEL 1)
130 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF1 | 7 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-23 17:24 | 2:19 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 1)
133 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF1 | 6 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-23 19:47 | 1:04 | K (Dependency group K child); Y (M9884A - CHANNEL 1)
136 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF1 | 9 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-01 18:20 | 0:53 | I (ST5); K (Dependency group V parent); Y (M9884A - CHANNEL 1)
141 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF1 | 43 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-02 06:50 | 0:48 | I (514;ST5 - all); K (Dependency group V child); Y (M9884A - CHANNEL 1)
142 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF1 | 42 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-02 07:38 | 0:34 | I (ST5); K (Dependency group V child); Y (M9884A - CHANNEL 1)
145 | ET54730 | ACLR-Testing | Channel Flatness | RF1 | 6 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-16 | 2026-01-22 06:30 | 0:24 | I (514); Y (M9884A - CHANNEL 1)
146 | ET54730 | ACLR-Testing | Channel Flatness | RF1 | 3 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-16 | 2026-01-22 06:59 | 0:01 | Y (M9884A - CHANNEL 1)
147 | ET54730 | ACLR-Testing | Functional Tests | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-23 20:52 | 0:03 | Y (M9884A - CHANNEL 1)
151 | ET54730 | ACLR-Testing | Phase Measurements | RF1 | 34 | 2 | 2 |  | 32 | PASSED | gdrss3-54 | 2026-01-23 20:56 | 0:11 | I (514); K (Dependency group G child); Y (M9884A - CHANNEL 1)
152 | ET57033 | PNA-X | Phase Measurements | RF1 | 33 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 17:22 | 0:26 | I (514); K (Dependency group G child); M (Diversity group E); Y (M9884A - CHANNEL 1)
153 | ET54730 | ACLR-Testing | Phase Measurements | RF1 | 32 | 2 | 2 |  | 32 | PASSED | gdrss3-54 | 2026-01-23 21:06 | 0:29 | K (Dependency group F child); Y (M9884A - CHANNEL 1)
154 | ET57033 | PNA-X | Phase Measurements | RF1 | 31 | 2 | 2 | 256 |  | PASSED | gdrss3-02 | 2026-01-22 17:50 | 0:25 | K (Dependency group F child); M (Diversity group D); Y (M9884A - CHANNEL 1)
155 | ET55857 | X-Mod | Functional Tests | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-22 | 2026-01-31 18:27 | 0:03 | Y (M9884A - CHANNEL 1)
157 | ET55857 | X-Mod | Switching Speed | RF1 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 18:30 | 0:36 | I (514); Y (M9884A - CHANNEL 1)
158 | ET55857 | X-Mod | Switching Speed | RF1 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 19:07 | 0:17 | Y (M9884A - CHANNEL 1)
160 | ET54730 | ACLR-Testing | Pulse Modulation | RF1 | 11 | 2 | 2 | 8192 | 94 | PASSED | gdrss3-54 | 2026-01-23 21:36 | 0:21 | Y (M9884A - CHANNEL 1)
162 | ET55857 | X-Mod | Pulse Modulation | RF1 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 19:24 | 0:29 | I (514); Y (M9884A - CHANNEL 1)
163 | ET55857 | X-Mod | Pulse Modulation | RF1 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 19:55 | 0:27 | Y (M9884A - CHANNEL 1)
175 | ET54730 | ACLR-Testing | Spectral | RF1 | 16 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-23 22:00 | 0:13 | I (514); Y (M9884A - CHANNEL 1)
176 | ET54730 | ACLR-Testing | Spectral | RF1 | 15 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-23 22:13 | 0:21 | I (514); Y (M9884A - CHANNEL 1)
177 | ET54730 | ACLR-Testing | Spectral | RF1 | 14 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-23 22:34 | 1:11 | I (514); Y (M9884A - CHANNEL 1)
178 | ET54730 | ACLR-Testing | Spectral | RF1 | 13 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-23 23:46 | 0:12 | I (520); Y (M9884A - CHANNEL 1)
179 | ET54730 | ACLR-Testing | Spectral | RF1 | 6 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-23 23:59 | 0:16 | Y (M9884A - CHANNEL 1)
180 | ET54730 | ACLR-Testing | Spectral | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-24 00:21 | 0:17 | Y (M9884A - CHANNEL 1)
181 | ET54730 | ACLR-Testing | Spectral | RF1 | 4 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-24 00:39 | 0:33 | Y (M9884A - CHANNEL 1)
182 | ET54730 | ACLR-Testing | Spectral | RF1 | 3 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-24 01:12 | 0:24 | Y (M9884A - CHANNEL 1)
185 | ET54730 | ACLR-Testing | Acpr | RF1 | 6 | 2 | 2 |  | 32 | PASSED | gdrss3-17 | 2026-01-24 08:08 | 0:41 | I (514); Y (M9884A - CHANNEL 1)
186 | ET54730 | ACLR-Testing | Acpr | RF1 | 4 | 2 | 2 |  | 32 | PASSED | gdrss3-17 | 2026-01-24 08:50 | 1:51 | Y (M9884A - CHANNEL 1)
187 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 29 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-23 05:03 | 0:05 | E; M (Diversity group A); Y (M9884A - CHANNEL 1)
188 | ET57033 | PNA-X | Amplitude Accuracy | RF1 | 21 | 2 | 2 | 512 |  | PASSED | gdrss3-68 | 2026-02-01 08:50 | 0:27 | A; M (Diversity group A); Y (M9884A - CHANNEL 1)
189 | Insert test plan: M9884A 1E62340462 | B; C; I (002); Q
190 | ET57033 | PNA-X | Functional Tests | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 18:16 | 0:02 | Y (M9884A - CHANNEL 2)
191 | ET57033 | PNA-X | Functional Tests | RF2 | 40 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 18:19 | 0:15 | Y (M9884A - CHANNEL 2)
197 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 3 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 18:36 | 0:28 | I (514); K (Dependency group J parent); M (Diversity group B); Y (M9884A - CHANNEL 2)
198 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 33 | 2 | 2 |  |  | PASSED | gdrss3-02 | 2026-01-22 19:06 | 0:05 | I (514); J (1EB); K (Dependency group J child); Y (M9884A - CHANNEL 2)
201 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 73 | 2 | 2 |  |  | PASSED | gdrss3-09 | 2026-01-22 20:55 | 0:40 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 2)
203 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 2 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-22 21:37 | 0:30 | K (Dependency group K parent); M (Diversity group A); Y (M9884A - CHANNEL 2)
204 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 22 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-22 22:10 | 3:00 | E; Y (M9884A - CHANNEL 2)
205 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 32 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-23 01:13 | 0:04 | J (1EA); K (Dependency group K child); Y (M9884A - CHANNEL 2)
208 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 72 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-23 01:19 | 0:32 | K (Dependency group K child); Y (M9884A - CHANNEL 2)
214 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF2 | 7 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-24 10:47 | 2:18 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 2)
217 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF2 | 6 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-24 13:10 | 1:04 | K (Dependency group K child); Y (M9884A - CHANNEL 2)
224 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF2 | 43 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-02 09:03 | 0:20 | I (514;ST5 - all); K (Dependency group V child); Y (M9884A - CHANNEL 2)
225 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF2 | 42 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-02 09:24 | 0:38 | I (ST5); K (Dependency group V child); Y (M9884A - CHANNEL 2)
228 | ET54730 | ACLR-Testing | Channel Flatness | RF2 | 6 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-53 | 2026-01-20 14:49 | 0:07 | I (514); Y (M9884A - CHANNEL 2)
229 | ET54730 | ACLR-Testing | Channel Flatness | RF2 | 3 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-53 | 2026-01-20 14:58 | 0:07 | Y (M9884A - CHANNEL 2)
230 | ET54730 | ACLR-Testing | Functional Tests | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-24 14:15 | 0:02 | Y (M9884A - CHANNEL 2)
234 | ET54730 | ACLR-Testing | Phase Measurements | RF2 | 34 | 2 | 2 |  | 32 | PASSED | gdrss3-17 | 2026-01-24 14:18 | 0:10 | I (514); K (Dependency group G child); Y (M9884A - CHANNEL 2)
235 | ET57033 | PNA-X | Phase Measurements | RF2 | 33 | 2 | 2 |  |  | PASSED | gdrss3-09 | 2026-01-23 01:53 | 0:28 | I (514); K (Dependency group G child); M (Diversity group E); Y (M9884A - CHANNEL 2)
236 | ET54730 | ACLR-Testing | Phase Measurements | RF2 | 32 | 2 | 2 |  | 32 | PASSED | gdrss3-17 | 2026-01-24 14:29 | 0:27 | K (Dependency group F child); Y (M9884A - CHANNEL 2)
237 | ET57033 | PNA-X | Phase Measurements | RF2 | 31 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-23 02:22 | 0:31 | K (Dependency group F child); M (Diversity group D); Y (M9884A - CHANNEL 2)
238 | ET55857 | X-Mod | Functional Tests | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-22 | 2026-01-31 21:05 | 0:03 | Y (M9884A - CHANNEL 2)
240 | ET55857 | X-Mod | Switching Speed | RF2 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 21:08 | 0:36 | I (514); Y (M9884A - CHANNEL 2)
241 | ET55857 | X-Mod | Switching Speed | RF2 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 21:48 | 0:18 | Y (M9884A - CHANNEL 2)
243 | ET54730 | ACLR-Testing | Pulse Modulation | RF2 | 11 | 2 | 2 | 8192 | 94 | PASSED | gdrss3-17 | 2026-01-24 14:57 | 0:21 | Y (M9884A - CHANNEL 2)
245 | ET55857 | X-Mod | Pulse Modulation | RF2 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 22:06 | 0:29 | I (514); Y (M9884A - CHANNEL 2)
246 | ET55857 | X-Mod | Pulse Modulation | RF2 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 22:36 | 0:27 | Y (M9884A - CHANNEL 2)
258 | ET54730 | ACLR-Testing | Spectral | RF2 | 16 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-24 15:22 | 0:12 | I (514); Y (M9884A - CHANNEL 2)
259 | ET54730 | ACLR-Testing | Spectral | RF2 | 15 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-24 15:35 | 0:20 | I (514); Y (M9884A - CHANNEL 2)
260 | ET54730 | ACLR-Testing | Spectral | RF2 | 14 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-24 15:56 | 1:11 | I (514); Y (M9884A - CHANNEL 2)
261 | ET54730 | ACLR-Testing | Spectral | RF2 | 13 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-24 17:07 | 0:13 | I (520); Y (M9884A - CHANNEL 2)
262 | ET54730 | ACLR-Testing | Spectral | RF2 | 6 | 2 | 2 |  |  | PASSED | gdrss3-17 | 2026-01-24 17:21 | 0:15 | Y (M9884A - CHANNEL 2)
263 | ET54730 | ACLR-Testing | Spectral | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss3-56 | 2026-01-25 14:29 | 0:17 | Y (M9884A - CHANNEL 2)
264 | ET54730 | ACLR-Testing | Spectral | RF2 | 4 | 2 | 2 |  |  | PASSED | gdrss3-56 | 2026-01-25 14:47 | 0:32 | Y (M9884A - CHANNEL 2)
265 | ET54730 | ACLR-Testing | Spectral | RF2 | 3 | 2 | 2 |  |  | PASSED | gdrss3-56 | 2026-01-25 15:19 | 0:44 | Y (M9884A - CHANNEL 2)
268 | ET54730 | ACLR-Testing | Acpr | RF2 | 6 | 2 | 2 |  | 32 | PASSED | gdrss3-54 | 2026-01-25 18:43 | 0:41 | I (514); Y (M9884A - CHANNEL 2)
269 | ET54730 | ACLR-Testing | Acpr | RF2 | 4 | 2 | 2 |  | 32 | PASSED | gdrss3-54 | 2026-01-25 19:27 | 1:50 | Y (M9884A - CHANNEL 2)
270 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 29 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-23 05:09 | 0:05 | E; M (Diversity group A); Y (M9884A - CHANNEL 2)
271 | ET57033 | PNA-X | Amplitude Accuracy | RF2 | 21 | 2 | 2 | 512 |  | PASSED | gdrss3-68 | 2026-02-01 09:22 | 0:10 | A; M (Diversity group A); Y (M9884A - CHANNEL 2)
272 | Insert test plan: M9884A 1E62340463 | B; C; I (003); Q
273 | ET57033 | PNA-X | Functional Tests | RF3 | 5 | 2 | 2 |  |  | PASSED | gdrss3-09 | 2026-01-23 02:55 | 0:02 | Y (M9884A - CHANNEL 3)
274 | ET57033 | PNA-X | Functional Tests | RF3 | 40 | 2 | 2 |  |  | PASSED | gdrss3-09 | 2026-01-23 02:59 | 0:15 | Y (M9884A - CHANNEL 3)
280 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 3 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-23 04:36 | 0:26 | I (514); K (Dependency group J parent); M (Diversity group B); Y (M9884A - CHANNEL 3)
281 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 33 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-23 05:50 | 0:05 | I (514); J (1EB); K (Dependency group J child); Y (M9884A - CHANNEL 3)
284 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 73 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-23 05:56 | 0:20 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 3)
286 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 2 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-23 06:50 | 0:29 | K (Dependency group K parent); M (Diversity group A); Y (M9884A - CHANNEL 3)
287 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 22 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-23 07:55 | 2:36 | E; Y (M9884A - CHANNEL 3)
288 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 32 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-23 11:49 | 0:05 | J (1EA); K (Dependency group K child); Y (M9884A - CHANNEL 3)
291 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 72 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-23 11:54 | 0:30 | K (Dependency group K child); Y (M9884A - CHANNEL 3)
297 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF3 | 7 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-25 21:18 | 2:18 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 3)
300 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF3 | 6 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-25 23:40 | 1:04 | K (Dependency group K child); Y (M9884A - CHANNEL 3)
307 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF3 | 43 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-02 10:04 | 0:21 | I (514;ST5 - all); K (Dependency group V child); Y (M9884A - CHANNEL 3)
308 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF3 | 42 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-02 10:27 | 0:39 | I (ST5); K (Dependency group V child); Y (M9884A - CHANNEL 3)
311 | ET54730 | ACLR-Testing | Channel Flatness | RF3 | 6 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-53 | 2026-01-20 15:05 | 0:28 | I (514); Y (M9884A - CHANNEL 3)
312 | ET54730 | ACLR-Testing | Channel Flatness | RF3 | 3 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-53 | 2026-01-20 15:35 | 0:05 | Y (M9884A - CHANNEL 3)
313 | ET54730 | ACLR-Testing | Functional Tests | RF3 | 5 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 00:45 | 0:02 | Y (M9884A - CHANNEL 3)
317 | ET54730 | ACLR-Testing | Phase Measurements | RF3 | 34 | 2 | 2 |  | 32 | PASSED | gdrss3-54 | 2026-01-26 00:48 | 0:10 | I (514); K (Dependency group G child); Y (M9884A - CHANNEL 3)
318 | ET57033 | PNA-X | Phase Measurements | RF3 | 33 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-23 12:26 | 0:23 | I (514); K (Dependency group G child); M (Diversity group E); Y (M9884A - CHANNEL 3)
319 | ET54730 | ACLR-Testing | Phase Measurements | RF3 | 32 | 2 | 2 |  | 32 | PASSED | gdrss3-54 | 2026-01-26 00:59 | 0:28 | K (Dependency group F child); Y (M9884A - CHANNEL 3)
320 | ET57033 | PNA-X | Phase Measurements | RF3 | 31 | 2 | 2 | 256 |  | PASSED | gdrss3-03 | 2026-01-24 18:54 | 0:26 | K (Dependency group F child); M (Diversity group D); Y (M9884A - CHANNEL 3)
321 | ET55857 | X-Mod | Functional Tests | RF3 | 5 | 2 | 2 |  |  | PASSED | gdrss3-22 | 2026-01-31 23:45 | 0:03 | Y (M9884A - CHANNEL 3)
323 | ET55857 | X-Mod | Switching Speed | RF3 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-01-31 23:49 | 0:29 | I (514); Y (M9884A - CHANNEL 3)
324 | ET55857 | X-Mod | Switching Speed | RF3 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-02-01 00:29 | 0:17 | Y (M9884A - CHANNEL 3)
326 | ET54730 | ACLR-Testing | Pulse Modulation | RF3 | 11 | 2 | 2 | 8192 | 94 | PASSED | gdrss3-54 | 2026-01-26 01:28 | 0:20 | Y (M9884A - CHANNEL 3)
328 | ET55857 | X-Mod | Pulse Modulation | RF3 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-02-01 00:47 | 0:29 | I (514); Y (M9884A - CHANNEL 3)
329 | ET55857 | X-Mod | Pulse Modulation | RF3 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-02-01 01:18 | 0:27 | Y (M9884A - CHANNEL 3)
341 | ET54730 | ACLR-Testing | Spectral | RF3 | 16 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 01:51 | 0:12 | I (514); Y (M9884A - CHANNEL 3)
342 | ET54730 | ACLR-Testing | Spectral | RF3 | 15 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 02:04 | 0:20 | I (514); Y (M9884A - CHANNEL 3)
343 | ET54730 | ACLR-Testing | Spectral | RF3 | 14 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 02:25 | 1:10 | I (514); Y (M9884A - CHANNEL 3)
344 | ET54730 | ACLR-Testing | Spectral | RF3 | 13 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 03:35 | 0:12 | I (520); Y (M9884A - CHANNEL 3)
345 | ET54730 | ACLR-Testing | Spectral | RF3 | 6 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 03:48 | 0:15 | Y (M9884A - CHANNEL 3)
346 | ET54730 | ACLR-Testing | Spectral | RF3 | 5 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 04:07 | 0:17 | Y (M9884A - CHANNEL 3)
347 | ET54730 | ACLR-Testing | Spectral | RF3 | 4 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 04:24 | 0:33 | Y (M9884A - CHANNEL 3)
348 | ET54730 | ACLR-Testing | Spectral | RF3 | 3 | 2 | 2 |  |  | PASSED | gdrss3-54 | 2026-01-26 04:57 | 0:24 | Y (M9884A - CHANNEL 3)
351 | ET54730 | ACLR-Testing | Acpr | RF3 | 6 | 2 | 2 |  | 32 | PASSED | gdrss3-54 | 2026-01-26 05:22 | 0:42 | I (514); Y (M9884A - CHANNEL 3)
352 | ET54730 | ACLR-Testing | Acpr | RF3 | 4 | 2 | 2 |  | 32 | PASSED | gdrss3-54 | 2026-01-26 06:05 | 1:50 | Y (M9884A - CHANNEL 3)
353 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 29 | 2 | 2 | 512 |  | PASSED | gdrss3-02 | 2026-01-29 10:00 | 0:08 | E; M (Diversity group A); Y (M9884A - CHANNEL 3)
354 | ET57033 | PNA-X | Amplitude Accuracy | RF3 | 21 | 2 | 2 | 512 |  | PASSED | gdrss3-68 | 2026-02-01 09:40 | 0:10 | A; M (Diversity group A); Y (M9884A - CHANNEL 3)
355 | Insert test plan: M9884A 1E62340464 | B; C; I (004); Q
356 | ET57033 | PNA-X | Functional Tests | RF4 | 5 | 2 | 2 |  |  | PASSED | gdrss3-09 | 2026-01-27 15:41 | 0:02 | Y (M9884A - CHANNEL 4)
357 | ET57033 | PNA-X | Functional Tests | RF4 | 40 | 2 | 2 |  |  | PASSED | gdrss3-09 | 2026-01-27 15:45 | 0:15 | Y (M9884A - CHANNEL 4)
363 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 3 | 2 | 2 |  |  | PASSED | gdrss3-04 | 2026-01-30 12:23 | 0:28 | I (514); K (Dependency group J parent); M (Diversity group B); Y (M9884A - CHANNEL 4)
364 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 33 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-24 21:15 | 0:04 | I (514); J (1EB); K (Dependency group J child); Y (M9884A - CHANNEL 4)
367 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 73 | 2 | 2 |  |  | PASSED | gdrss3-03 | 2026-01-24 21:55 | 0:24 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 4)
369 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 2 | 2 | 2 | 256 |  | PASSED | gdrss3-04 | 2026-01-30 13:09 | 0:35 | K (Dependency group K parent); M (Diversity group A); Y (M9884A - CHANNEL 4)
370 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 22 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-27 16:03 | 3:01 | E; Y (M9884A - CHANNEL 4)
371 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 32 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-27 19:10 | 0:04 | J (1EA); K (Dependency group K child); Y (M9884A - CHANNEL 4)
374 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 72 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-27 19:16 | 0:31 | K (Dependency group K child); Y (M9884A - CHANNEL 4)
380 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF4 | 7 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-28 16:14 | 2:17 | I (514); K (Dependency group J child); Y (M9884A - CHANNEL 4)
383 | ET54730 | ACLR-Testing | Amplitude Accuracy | RF4 | 6 | 2 | 2 |  |  | PASSED | gdrss3-56 | 2026-01-30 15:34 | 1:02 | K (Dependency group K child); Y (M9884A - CHANNEL 4)
390 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF4 | 43 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-02 11:08 | 0:20 | I (514;ST5 - all); K (Dependency group V child); Y (M9884A - CHANNEL 4)
391 | ET57381 | Peanuts Phase Noise | PhaseNoiseG2.4 | RF4 | 42 | 2 | 2 |  |  | PASSED | pnoise101 | 2026-03-02 11:29 | 1:10 | I (ST5); K (Dependency group V child); Y (M9884A - CHANNEL 4)
394 | ET54730 | ACLR-Testing | Channel Flatness | RF4 | 6 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-51 | 2026-01-28 19:39 | 0:14 | I (514); Y (M9884A - CHANNEL 4)
395 | ET54730 | ACLR-Testing | Channel Flatness | RF4 | 3 | 2 | 2 | 73728 | 32 | PASSED | gdrss3-51 | 2026-01-28 19:53 | 0:01 | Y (M9884A - CHANNEL 4)
396 | ET54730 | ACLR-Testing | Functional Tests | RF4 | 5 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-28 20:37 | 0:02 | Y (M9884A - CHANNEL 4)
400 | ET54730 | ACLR-Testing | Phase Measurements | RF4 | 34 | 2 | 2 |  | 32 | PASSED | gdrss3-51 | 2026-01-28 20:44 | 0:09 | I (514); K (Dependency group G child); Y (M9884A - CHANNEL 4)
401 | ET57033 | PNA-X | Phase Measurements | RF4 | 33 | 2 | 2 |  |  | PASSED | gdrss3-09 | 2026-01-27 19:49 | 0:28 | I (514); K (Dependency group G child); M (Diversity group E); Y (M9884A - CHANNEL 4)
402 | ET54730 | ACLR-Testing | Phase Measurements | RF4 | 32 | 2 | 2 |  | 32 | PASSED | gdrss3-51 | 2026-01-28 20:53 | 0:34 | K (Dependency group F child); Y (M9884A - CHANNEL 4)
403 | ET57033 | PNA-X | Phase Measurements | RF4 | 31 | 2 | 2 | 256 |  | PASSED | gdrss3-09 | 2026-01-27 20:18 | 0:29 | K (Dependency group F child); M (Diversity group D); Y (M9884A - CHANNEL 4)
404 | ET55857 | X-Mod | Functional Tests | RF4 | 5 | 2 | 2 |  |  | PASSED | gdrss3-22 | 2026-02-01 02:28 | 0:02 | Y (M9884A - CHANNEL 4)
406 | ET55857 | X-Mod | Switching Speed | RF4 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-02-01 03:31 | 0:38 | I (514); Y (M9884A - CHANNEL 4)
407 | ET55857 | X-Mod | Switching Speed | RF4 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-02-01 04:09 | 0:18 | Y (M9884A - CHANNEL 4)
409 | ET54730 | ACLR-Testing | Pulse Modulation | RF4 | 11 | 2 | 2 | 8192 | 94 | PASSED | gdrss3-51 | 2026-01-28 21:28 | 0:20 | Y (M9884A - CHANNEL 4)
411 | ET55857 | X-Mod | Pulse Modulation | RF4 | 4 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-02-01 04:28 | 0:30 | I (514); Y (M9884A - CHANNEL 4)
412 | ET55857 | X-Mod | Pulse Modulation | RF4 | 3 | 2 | 2 | 8 |  | PASSED | gdrss3-22 | 2026-02-01 05:01 | 0:27 | Y (M9884A - CHANNEL 4)
424 | ET54730 | ACLR-Testing | Spectral | RF4 | 16 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-28 21:49 | 0:12 | I (514); Y (M9884A - CHANNEL 4)
425 | ET54730 | ACLR-Testing | Spectral | RF4 | 15 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-28 22:02 | 0:19 | I (514); Y (M9884A - CHANNEL 4)
426 | ET54730 | ACLR-Testing | Spectral | RF4 | 14 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-28 22:22 | 1:08 | I (514); Y (M9884A - CHANNEL 4)
427 | ET54730 | ACLR-Testing | Spectral | RF4 | 13 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-28 23:35 | 0:11 | I (520); Y (M9884A - CHANNEL 4)
428 | ET54730 | ACLR-Testing | Spectral | RF4 | 6 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-28 23:47 | 0:14 | Y (M9884A - CHANNEL 4)
429 | ET54730 | ACLR-Testing | Spectral | RF4 | 5 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-29 00:02 | 0:16 | Y (M9884A - CHANNEL 4)
430 | ET54730 | ACLR-Testing | Spectral | RF4 | 4 | 2 | 2 |  |  | PASSED | gdrss3-56 | 2026-01-30 17:04 | 0:31 | Y (M9884A - CHANNEL 4)
431 | ET54730 | ACLR-Testing | Spectral | RF4 | 3 | 2 | 2 |  |  | PASSED | gdrss3-51 | 2026-01-29 11:46 | 0:22 | Y (M9884A - CHANNEL 4)
434 | ET54730 | ACLR-Testing | Acpr | RF4 | 6 | 2 | 2 |  | 32 | PASSED | gdrss3-51 | 2026-01-29 12:08 | 0:42 | I (514); Y (M9884A - CHANNEL 4)
435 | ET54730 | ACLR-Testing | Acpr | RF4 | 4 | 2 | 2 |  | 32 | PASSED | gdrss3-13 | 2026-01-31 14:57 | 1:51 | Y (M9884A - CHANNEL 4)
436 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 29 | 2 | 2 | 512 |  | PASSED | gdrss3-03 | 2026-01-27 20:50 | 0:05 | E; M (Diversity group A); Y (M9884A - CHANNEL 4)
437 | ET57033 | PNA-X | Amplitude Accuracy | RF4 | 21 | 2 | 2 | 512 |  | PASSED | gdrss3-68 | 2026-02-01 09:52 | 0:10 | A; M (Diversity group A); Y (M9884A - CHANNEL 4)
439 | ET54791 | POSTPONEMENT | Functional Tests | CPU | 16 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-03-03 17:16 | 0:01 | A; G (Ship It)
440 | ET54791 | POSTPONEMENT | MCS3 Reconfig | CPU | 7 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-03-03 17:24 | 0:02 | A; G (Ship It)
441 | ET54791 | POSTPONEMENT | MCS3 Reconfig | CPU | 6 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-03-03 17:29 | 0:04 | A; G (Ship It); I (PCH)
442 | ET54791 | POSTPONEMENT | CustomerInit | CPU | 2 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-03-03 17:34 | 0:09 | A; G (Ship It)
443 | ET54791 | POSTPONEMENT | CustomerInit | CPU | 3 | 2 | 2 |  |  | PASSED | gdrss96 | 2026-03-03 17:44 | 0:00 | A; G (Ship It)
444 | ET54791 | POSTPONEMENT | Functional Tests | RF1 | 5 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 11:47 | 0:03 | A; G (Ship It); Y (M9884A - CHANNEL 1)
445 | ET54791 | POSTPONEMENT | Functional Tests | RF2 | 5 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 11:55 | 0:02 | A; G (Ship It); Y (M9884A - CHANNEL 2)
446 | ET54791 | POSTPONEMENT | Functional Tests | RF3 | 5 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 12:00 | 0:02 | A; G (Ship It); Y (M9884A - CHANNEL 3)
447 | ET54791 | POSTPONEMENT | Functional Tests | RF4 | 5 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 12:10 | 0:02 | A; G (Ship It); Y (M9884A - CHANNEL 4)
448 | ET54791 | POSTPONEMENT | Functional Tests | RF1 | 17 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 12:15 | 0:02 | A; G (Ship It); Y (M9884A - CHANNEL 1)
449 | ET54791 | POSTPONEMENT | Functional Tests | RF2 | 17 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 12:25 | 0:01 | A; G (Ship It); Y (M9884A - CHANNEL 2)
450 | ET54791 | POSTPONEMENT | Functional Tests | RF3 | 17 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 12:34 | 0:01 | A; G (Ship It); Y (M9884A - CHANNEL 3)
451 | ET54791 | POSTPONEMENT | Functional Tests | RF4 | 17 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 12:42 | 0:01 | A; G (Ship It); Y (M9884A - CHANNEL 4)
452 | ET54791 | POSTPONEMENT | FinalConfiguration | CPU | 2 | 2 | 2 |  |  | PASSED | gdrss160 | 2026-03-04 12:59 | 0:00 | A; G (Ship It); J (A6J;AMG - any)
453 | ET54791 | POSTPONEMENT | Functional Tests | CPU | 34 | 2 | 2 |  |  | PASSED | gdrss150 | 2026-03-04 17:07 | 0:00 | A; G (Ship It)
455 | ET53925 | HiPot EI | RST |  | 3 | 2 | 2 |  |  | PASSED | sshipot01 | 2026-03-05 14:35 | 0:01 | G (Ship It)